## PCD-selected
Delaware County - Margaretville Memorial Hospital
2023 Workplan
Planning Report Liaison | Thao M. Doan, MPH, DrPH
E-mail: | Thao.Doan@wmchealth.org
Priority | Focus Area (select one from drop down list) | Goal Focus Area (select one from drop down list) | Objectives through 2024 | Disparities | Interventions | Family of Measures | By December 2023, we will have completed . . . | Implementation Partner (Please select one partner from the dropdown list per row) | Partner Role(s) and Resources
Prevent Chronic Diseases | Focus Area 4: Preventive care and management | Goal 4.3 Promote evidence-based care to prevent and manage chronic diseases including asthma, arthritis, cardiovascular disease, diabetes and prediabetes and obesity | Objective 4.3.1: Increase early detection of chronic lower respiratory disease (CLRD), which includes asthma and COPD (chronic obstructive pulmonary disease) by 100 new patients, based on 2022 baseline | Individuals living in poverty, have unmet SDOH needs, and a lack of access to critical health services; the aging (65+) and the rapidly aging population with significant health inequities, health care disparities, and health illiteracy challenges. | *Identify, track, and provide pulmonary screening and care coordination to CLRD patients | Data to be collected about enrolled patients: • Diagnosis of CLRD/pulmonary function screening • Demographics data on race, ethnicity, gender, age and other background data • SDOH needs • Referral source to the program • Type of connectivity/care coordination provided | *Screen and enroll at least 50 CLRD patients. *Provide all undiagnosed patients pulmonary function test and/or a chest x-ray to document disease stage and diagnosis and establish baseline volume. *Follow up to baseline respiratory status with Peak Flow measurements and spirometry readings every six months for at least 50 patients. *Conduct a SDOH assessment on at least 50 enrollees at intake and provide care coordination to address identified SDOH needs. | Community-based organizations | Delaware County Office for the Aging, the Ulster County Office for the Aging, and the Catskill Hudson Area Health Education Center - all partners will work collaboratively with Margaretville Hospital providers through regular meetings, community events, and outreach efforts to raise awareness for the community at large about these services.
Prevent Chronic Diseases | Focus Area 4: Preventive care and management | Goal 4.4 In the community setting, improve self-management skills for individuals with chronic diseases, including asthma, arthritis, cardiovascular disease, diabetes and prediabetes and obesity | Objective 4.4.1 Increase the percentage of adults with chronic conditions (arthritis, asthma, CVD, diabetes, CKD, cancer) who have taken a course or class to learn how to manage their condition (70% of those diagnosed/screened positive for CLRD, starting in 2023) | Individuals living in poverty, have unmet SDOH needs, and a lack of access to critical health services; the aging (65+) and the rapidly aging population with significant health inequities, health care disparities, and health illiteracy challenges. | *Provide education and training to CLRD patients to increase their knowledge in self-managing CLRD conditions *Provide training to nursing and provider staff members, including future staff, to generate a well-informed and confident provider workforce | Data to be collected about CLRD self-management training program: • Number of participating patients enrolled in and graduated from the six-month program • Number of CLRD exacerbation flare-ups or ED visits • Changes in patient knowledge, attitude, behavior, health status, and health care utilization. Data to be collected about the staff training program: • Number of staff trained online via NetLearning • Respondents’ feedback as part of the PDSA process | *Host quarterly Community Workshops both virtually and in-person at Margaretville Hospital. Community Workshop topics include: • COPD/Emphysema Management • CPAP Maintenance • O2 Concentrator Maintenance • Asthma Management • Smoking/Vaping Prevention/Cessation *Host health fairs at local events, including farmers markets, the annual Cauliflower Festival and Meredith Dairy Festival, the Delaware County Fair, and various monthly Chamber of Commerce and Rotary Club meetings. Local events are most accessible and most attended during the summer months. *Conduct a six-month education program for two cohorts of up to 25 patients. Education program will be held bi-monthly and offered via in-person and remote (i.e., Zoom) according to patient cohort needs. *Train a minimum of 80% of Margaretville nursing and provider staff (ED and Acute) and external providers on the learning management system (NetLearning Platform) about the proposed program (i.e., purpose of the project; inclusion criteria; Chronic Care Management model, and referral process). | Community-based organizations | Delaware County Office for the Aging, the Ulster County Office for the Aging, and the Catskill Hudson Area Health Education Center - all partners will work collaboratively with Margaretville Hospital providers through regular meetings, community events, and outreach efforts to raise awareness for the community at large about these services.

## PWPMSUD-selected
Delaware County - Margaretville Memorial Hospital
2023 Workplan
Planning Report Liaison | Thao M. Doan, MPH, DrPH
E-mail: | Thao.Doan@wmchealth.org
Priority | Focus Area | Goal | Objectives through 2024 | Disparities | Interventions | Family of Measures | By December 2023, we will have completed . . . | Implementation Partner (Please select one partner from the dropdown list per row) | Partner Role(s) and Resources
Promote Well-Being and Prevent Mental and Substance Use Disorders | Focus Area 2: Prevent Mental and Substance User Disorders | Goal 2.2 Prevent opioid overdose deaths | Objective 2.2.1 Reduce the age-adjusted overdose deaths involving any opioid by 7%, using 2022 baseline | N/A | *Intervention 2.2.2 Increase availability of/access to overdose reversal (Naloxone) trainings to prescribers, pharmacists and consumers | • Number of providers, paraprofessional staff, and community members (non-providers) who participated in direct substance use disorder education or training activities including: Mental health first aid, Naloxone training, Opioid prescribing guidelines, and Stigma reduction • Number of providers who have a Drug Addiction Treatment Act 2000 (DATA) waiver to prescribe buprenorphine-containing products for medication-assisted treatment (MAT) • Number of providers who have prescribed medications used to treat OUD • Number of non-fatal opioid overdoses • Number of fatal opioid overdoses • Number of patients receiving Medication-Assisted Treatment (with or without psychosocial therapy) • Number of patients with SUD/OUD treatment other than MAT • Number of service delivery sites that offered harm reduction services including: naloxone access, syringe services, fentanyl test strips, sex worker services, and safe smoking Kits | Reduce the age-adjusted overdose deaths involving any opioid by 3%, using 2022 baseline | Community-based organizations | • CAC – Catskill Addiction Coalition – will place a Certified Recovery Peer Advocates (CPRA) at the food pantry to screen and refer People Who Inject Drugs (PWUD) to SUD/OUD treatment. CAC also actively provides criminal justice education to law enforcement personnel and are designed to teach appropriate methods of working with people who use drugs, how to screen for substance use and behavioral health disorders, and how to refer individuals to treatment services • PSP – Project Safe Point - provides community opioid overdose prevention training, a syringe exchange program, peer and community health worker support, and Law Enforcement Assisted Diversion (LEAD). • SUNY Delhi School of Nursing - provides nursing students with professional development opportunities including internship possibilities, special projects, and continuing education possibilities. Lunch-and-learn programming will also be offered to train mental health workers and substance use workers about each other's disciplines. In addition, they will provide ongoing collection and reporting of data and activities.
Promote Well-Being and Prevent Mental and Substance Use Disorders | Focus Area 2: Prevent Mental and Substance User Disorders | Goal 2.2 Prevent opioid overdose deaths | Objective 2.2.4 Reduce all emergency department visits (including outpatients and admitted patients) involving any opioid overdose by 5%, using 2022 baseline | N/A | *Intervention 2.2.3 Promote and encourage prescriber education and familiarity with opioid prescribing guidelines and limits as imposed by NYS statutes and regulations *Intervention 2.2.5 Establish additional permanent safe disposal sites for prescription drugs and organized take-back days *Intervention 2.2.6 Integrate trauma informed approaches in training staff and implementing program and policy | • Number of providers, paraprofessional staff, and community members (non-providers) who participated in direct substance use disorder education or training activities including: Trauma-informed care training, Mental health first aid, Naloxone training, Opioid prescribing guidelines, and Stigma reduction • Number of permanent safe disposal sites for prescription • Number of SUD/OUD hospitalizations and/or emergency room visits • Number of service delivery sites that offer prevention, or recovery service, including: Prevention services (not including naloxone); Screening and/or assessment services, Infectious disease testing (i.e., HIV or HCV), Mental health treatment, and Recovery support services • Total number of individuals screened for SUD/OUD including those screened positive for alcohol or substance use, opioid overuse/misuse, methamphetamine overuse/misuse, and other substance overuse/misuse • Number of patients diagnosed with alcohol, substance, or methamphetamine use disorder • Number of patients with a diagnosis of substance use disorder (SUD) who were referred for SUD treatment. • Number of patients with a diagnosis of SUD who were referred to support services, including: Childcare, Employment services, Recovery housing, Transportation to treatment, Community Support Services (ie. FORDO, Wellness Coordinators, CRPAS, etc.), and Other than OUD/SUD Treatment (Inpatient, HCV, detox, etc.) • Number of individuals who received recovery support services | Reduce all emergency department visits (including outpatients and admitted patients) involving any opioid overdose by 2%, using 2022 baseline | Community-based organizations | • ADAC – Alcohol and Drug Abuse Council - provides trauma-informed care trainings, conducted in schools and for the community so people can recognize the signs for SUD/OUD, suicide, mental illness. • CHAHEC – Catskill Hudson Area Health Education Center - will host an annual symposium that will offer professional development and training opportunities for all levels of the nursing profession, as well as healthcare professionals, health professions educators, and health professions students. • PSP – Project Safe Point - provides community opioid overdose prevention training, a syringe exchange program, peer and community health worker support, and Law Enforcement Assisted Diversion (LEAD). • Samadhi - provides evidence-based mindfulness-based addiction recovery curriculum and trauma-informed care trainings by certified trauma-informed instructors. In addition, they provide trauma-informed meditation and relapse prevention programs. • SUNY Delhi School of Nursing - provides nursing students with professional development opportunities including internship possibilities, special projects, and continuing education possibilities. Lunch-and-learn programming will also be offered to train mental health workers and substance use workers about each other's disciplines. In addition, they will provide ongoing collection and reporting of data and activities.

## PHSE
Name of County - Organization(s)
2023 Workplan
Planning Report Liaison | Name of liaison | [5 empty] | Name of liaison
E-mail: | Email of liaison | [5 empty] | Email of liaison
Priority | Focus Area | Goal | Objectives through 2024 | Disparities | Interventions | Family of Measures | By December 2023, we will have completed . . . | Implementation Partner (Please select one partner from the dropdown list per row) | Partner Role(s) and Resources
Promote a Healthy and Safe Environment

## PHWIC
Name of County - Organization(s)
2023 Workplan
Planning Report Liaison | Name of liaison
E-mail: | Email of liaison
Priority | Focus Area | Goal | Objectives through 2024 | Disparities | Interventions | Family of Measures | By December 2023, we will have completed . . . | Projected Year 2 | Projected Year 3 Interventions | Implementation Partner (Please select one partner from the dropdown list per row) | Partner Role(s) and Resources
Promote Healthy Women, Infants and Children

## PCOMMD
Name of County - Organization(s)
2023 Workplan
Planning Report Liaison | Name of liaison
E-mail: | Email of liaison
Priority | Focus Area | Goal | Objectives through 2024 | Disparities | Interventions | Family of Measures | By December 2023, we will have completed . . . | Implementation Partner (Please select one partner from the dropdown list per row) | Partner Role(s) and Resources
Prevent Communicable Diseases

## Priorities (hidden)
Prevent Chronic Diseases
Promote a Healthy and Safe Environment
Promote Healthy Women, Infants and Children
Promote Well-Being and Prevent Mental and Substance Use Disorders
Prevent Communicable Diseases

## pcd_focus_area (hidden)
Focus Area 1: Healthy eating and food security
Focus Area 2: Physical activity
Focus Area 3: Tobacco prevention
Focus Area 4: Preventive care and management

## pcd_goal (hidden)
Goal 1.0 Reduce obesity and the risk of chronic disease
Goal 1.1 Increase access to healthy and affordable foods and beverages
Goal 1.2 Increase skills and knowledge to support healthy food and beverage choices
Goal 1.3 Increase food security
Goal 2.0 Reduce obesity and the risk of chronic diseases
Goal 2.1 Improve community environments that support active transportation and recreational physical activity for people of all ages and abilities.
Goal 2.2 Promote school, child care and worksite environments that increase physical activity
Goal 2.3 Increase access, for people of all ages and abilities, to indoor and/or outdoor places for physical activity.
Goal 3.1 Prevent initiation of tobacco use
Goal 3.2 Promote tobacco use cessation
Goal 3.3 Eliminate exposure to secondhand smoke
Goal 4.1 Increase cancer screening rates
Goal 4.2 Increase early detection of cardiovascular disease, diabetes, prediabetes and obesity
Goal 4.3 Promote evidence-based care to prevent and manage chronic diseases including asthma, arthritis, cardiovascular disease, diabetes and prediabetes and obesity
Goal 4.4 In the community setting, improve self-management skills for individuals with chronic diseases, including asthma, arthritis, cardiovascular disease, diabetes and prediabetes and obesity

## pwpsud_focus_area (hidden)
Focus Area 1: Promote Well-Being
Focus Area 2: Prevent Mental and Substance User Disorders

## pmpsud_goals (hidden)
Goal 1.1: Strengthen opportunities to build well-being and resilience across the lifespan
Goal 1.2 Facilitate supportive environments that promote respect and dignity for people of all ages
Goal 2.1: Prevent underage drinking and excessive alcohol consumption by adults
Goal 2.2 Prevent opioid overdose deaths
Goal 2.3 Prevent and address adverse childhood experiences
Goal 2.4 Reduce the prevalence of major depressive disorders
Goal 2.5 Prevent suicides
Goal 2.6 Reduce the mortality gap between those living with serious mental illnesses and the general population

## phse_focus_areas (hidden)
Focus Area 1: Injuries, Violence and Occupational Health
Focus Area 2: Outdoor Air Quality
Focus Area 3: Built and Indoor Environments
Focus Area 4: Water Quality
Focus Area 5: Food and Consumer Products

## phse_goals (hidden)
Goal 1.1: Reduce falls among vulnerable populations
Goal 1.2: Reduce violence by targeting prevention programs regularly to highest risk populations
Goal 1.3: Reduce occupational injuries and illness
Goal 1.4: Reduce traffic related injuries for pedestrians and bicyclists
Goal 2.1: Reduce exposure to outdoor air pollutants
Goal 3.1: Improve design and maintenance of the built environment to promote healthy lifestyles, sustainability, and adaptation to climate change
Goal 3.2: Promote healthy home and school environments
Goal 4.1: Protect water sources and ensure quality drinking water
Goal 4.2: Protect vulnerable waterbodies to reduce potential public health risks associated with exposure to recreational water
Goal 5.1: Raise awareness of the potential presence of chemical contaminants and promote strategies to reduce exposure
Goal 5.2: Improve food safety management

## phwic_focus_areas (hidden)
Focus Area 1: Maternal & Women's Health
Focus Area 2: Perinatal and Infant Health
Focus Area 3: Child and Adolescent Health, including children with special health care needs (CSHCN)

## phwic_goals (hidden)
Goal 1.1: Increase use of primary and preventive health care services by women, with a focus on women of reproductive age
Goal 1.2: Reduce Maternal Mortality and Morbidity
Goal 2.1: Reduce infant mortality and morbidity
Goal 2.2: Increase breastfeeding
Goal 3.1 Support and enhance children and adolescents’ social-emotional development and relationships
Goal 3.2: Increase supports for children and youth with special health care needs
Goal 3.3: Reduce dental caries among children
Goal 4.1 : Reduce racial, ethnic, economic, and geographic disparities in maternal and child health outcomes, and promote health equity for maternal and child health populations

## pcommd_focus_areas (hidden)
Focus Area 1: Vaccine Preventable Diseases
Focus Area 2: Human Immunodeficiency Virus (HIV)
Focus Area 3: Sexually Transmitted Infections
Focus Area 4: Hepatitis C Virus (HCV)
Focus Area 5: Antimicrobial Resistance and Healthcare-Associated Infections

## pcomm_goals (hidden)
Goal 1.1: Improve vaccination rates
Goal 1.2: Reduce Vaccination coverage disparities
Goal 2.1: Decrease HIV morbidity (new HIV diagnoses)
Goal 2.2: Increase viral suppression
Goal 3.1: Reduce the annual rate of growth for STIs
Goal 4.1: Increase the number of persons treated for Hepatitis C Virus
Goal 4.2: Reduce the number of new HCV cases among people who inject drugs
Goal 5.1: Improve infection control in healthcare facilities
Goal 5.2: Reduce infections caused by multidrug resistant organisms
Gold 5.3: Reduce inappropriate antibiotic use

## Partner List (hidden)
Dropdown
Advocates
Business
City government
College
Community-based organizations
Consumer
Faith
Federally qualified health care center
Headstart
Health Insurance Plans
Hospital
Housing
K-12 School
Law Enforcement
Legal services
Local governmental unit
Local health department
Media
Neighborhood leader
Office for the Aging
Participant
Patient
Pharmacies
Philanthropy
Providers
Senior Center
Social Services
Students
Transportation
Other (please describe partner and role(s) in column D)